## bug_tracking_template
ID | Severity | Priority | Module | Feature | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Reported Date | Target Fix Version | Fixed Date | Notes
BUG-001 | Critical | High | Explore | Topic Grid | Topics fail to load from Supabase | TopicsProvider returns empty list despite data existing in DB | 1. Open app 2. Navigate to Explore 3. Observe topic grid | Topics should display in 2-column grid | Topics grid shows loading or empty state | Open |  | 2026-07-28 | v1.0.0
BUG-002 | Major | High | Concept | Learning Objects | Learning objects fail to load | Concept screen shows no content for a concept with known data | 1. Navigate to a concept 2. Wait for content to load | Learning objects (cards/quizzes) should render | No content available yet message shown | Open |  | 2026-07-28 | v1.0.0
BUG-003 | Major | Medium | Auth | Google Sign-In | Google OAuth redirect fails on Android | Google Sign-In does not complete after selecting account | 1. Tap Sign in with Google 2. Select account | User should be authenticated and redirected to onboarding | Auth flow hangs or returns error | Open |  | 2026-07-28 | v1.0.0
BUG-004 | Minor | Low | Library | Saved Objects | Empty state text truncates on small screens | Start learning to build your library text wraps poorly on 360dp width devices | 1. Open Library with no saved objects 2. Observe text | Text should be fully visible and centered | Text is truncated or overflow rendered | Open |  | 2026-07-28 | v1.1.0
BUG-005 | Normal | Medium | Profile | Profile Switch | Profile screen overflow on 600px height devices | Profile switch screen Column overflows on small viewports | 1. Open profile switch on 600px height device 2. Scroll | Entire content should be scrollable | Bottom of screen clipped causing layout overflow | Open |  | 2026-07-28 | v1.0.0
BUG-006 | Normal | High | Home | Streak Display | Streak data not displayed on Home screen | Home screen shows mock streak instead of live profile streak data | 1. Open Home screen 2. Check streak section | Real streak from DB should display | Hardcoded mock data shown | Open |  | 2026-07-28 | v1.1.0
BUG-007 | Major | High | Concept | Quiz | Quiz answer validation has single question limit | Quiz widget only handles first question - no pagination through multiple questions | 1. Open concept with quiz 2. Answer question 1 3. Check for Q2 | Multiple questions should be answerable in sequence | Only first question displayed | Open |  | 2026-07-28 | v1.0.0
BUG-008 | Normal | Medium | Onboarding | Page Navigation | Onboarding page indicator animation lags | Page indicator dot animation stutters on slow devices | 1. Open onboarding 2. Swipe through pages 3. Observe dots | Smooth 300ms animated transitions | Animation visible stutter on low-end devices | Open |  | 2026-07-28 | v1.1.0
BUG-009 | Minor | Low | Explore | Search | Search field has no action handler | Search field is decorative - no search functionality implemented | 1. Open Explore 2. Type in search 3. Press enter | Search should filter topics | Nothing happens on search input | Open |  | 2026-07-28 | v1.1.0
BUG-010 | Normal | Medium | Concept | Difficulty Chip | Difficulty chip text case inconsistent | 'Beginner' vs 'beginner' display varies between list and detail views | 1. Open concept 2. Check chip | Consistent capitalization | List shows lowercase detail shows title case | Open |  | 2026-07-28 | v1.0.0
Release Cycle 1 (v1.0.0) - Foundation
Release Cycle 2 (v1.1.0) - Polish
Release Cycle 3 (v2.0.0) - AI Tutor